## List of Boughtout (hidden)
thyssenkrupp Industries India Ltd.
| Document Name | : Status of Lubrication Schedule for Bought-out Equipment |  |  |  | Rev-x
| Project | : Adani Mundra West Port |  |  |  | Date
| Client | : Adani Enterprises Ltd. |  |  |  | 2023-09-13
Sl. No. | tkII Drg /Doc. No. | HOWE doc no | Bought out items | Supplier | Status | Remarks
1 | 3M0078 C00 040 01 | B0300-450-E-ME-DG-092 | GA Drawing of Gearbox | Elecon | Not Received
2 | 3M0078 C00 050 01 | B0300-450-E-ME-DG-089 | GA Drawing of input coupling (Fluid coupling) | Fludiomat | Not Received
3 | 3M0078 C00 050 02 | B0300-450-E-ME-DG-090 | GA Drawing of input coupling (Flexible coupling) | Semiflex | NA
4 | 3M0078 C00 055 01 | B0300-450-E-ME-DG-091 | GA Drawing of output coupling | Elecon | Not Received
4a | 3M0078 C00 055 02 | B0300-450-E-ME-DG-141 | GA Drawing of output coupling for Movable Head | Elecon | Not Received
5 | 3M0078 C00 060 01 | B0300-450-E-ME-DG-093 | GA Drawing of Drum Brakes | Galvi | Not Received
6 | 3M0078 C00 060 03 | B0300-450-E-ME-DG-094 | GA Drawing of Disc Brakes | Kateel | Not Received
7 | 3M0078 C00 070 01 | B0300-450-E-ME-Ds-001 | Belting Datasheet for trough conveyors | Continental | NA
8 | 3M0078 C00 422 01 | B0300-450-E-ME-DG-095 | GA Drawing of Internal scraper | Hosch | NA
9 | 3M0078 C00 422 03 | B0300-450-E-ME-DG-096 | GA Drawing of external scraper | Hosch | NA
10 | 3M0078 C00 422 04 | B0300-450-E-ME-DG-097 | GA Drawing of Skirt seal | Thejo | NA
11 | 3M0078 C11 414 03 | B0300-450-E-ME-DG-115 | GA of Geared motor for Movable Head | PBL | Not Received
12 | 3M0078 C11 414 04 | B0300-450-E-ME-DG-116 | GA of Electro-hydraulic Rail clamp for Movable Head | Matchless | Not Received
13 | 3M0078 I00 000 01 | B0300-450-E-ME-DG-105 | GA Drawing and Datasheet of Online Sampling System | FLSmidth | Not Received
14 | 3M0078 J30 130 01 | B0300-450-E-ME-DG-107 | GA Drawing of Manual Slide Gates | Demech | Not Received
15 | 3M0078 J30 131 01 | B0300-450-E-ME-DG-106 | GA drawing of Diverter gates | Merit | Not Received
16 | 3M0078 J50 141 01 | B0300-450-E-ME-DG-109 | GA Drawing of Rack and pinion gate | Demech | Not Received | Truncated
17 | 3M0078 J60 137 01 | B0300-450-E-ME-DG-108 | GA Drawing of Hyd. Clamshell Gate | Merit | Not Received
18 | 3M0078 PC1 070 01 | B0300-450-E-ME-DS-002 | Belting Datasheet for pipe conveyors | Continental | NA
19 | 3M0078 V10 000 01 | B0300-450-E-ME-DG-101 | GA Drawing & Data sheet of Belt weigh scale | Thermofisher | NA
20 | 3M0078 V10 000 02 | B0300-450-E-ME-DG-102 | GA Drawing & Data sheet of Rip Detection & Health monitoring System | Continental | NA
21 | 3M0078 W20 000 01 | B0300-450-E-ME-DG-104 | GA Drawing of Inline Magnetic Separator | Prayas | Not Received
22 | 3M0078 W40 000 01 | B0300-450-E-ME-DG-100 | GA Drawing & Data sheet of Metal Detector | Thermofisher | NA
23 | 3M0078 W40 000 02 | B0300-450-E-ME-DG-103 | GA Drawing & Data sheet of Static Weighment System | Rick Lake | Not Received
24 | 3M0078 Y20 000 01 | B0300-450-E-ME-DG-098 | GA Drawing of Electric hoist | Century | Not Received
25 | 3M0078 Y20 000 02 | B0300-450-E-ME-DG-099 | GA Drawing of Manual hoist | Century | Not Received
26 | 3M0078 Y30 000 01 | B0300-450-E-ME-DG-117 | GA Drawing of Motorized winch | Century | Not Received
27 | 3M0078 X50 000 01 | B0300-450-E-ME-DG-139 | GA Drawing of Passenger cum Goods Elevator | Metro | Not Received
28 | 3M0078 C00 453 01 | - | Hydraulic Jack and Hand Pump With Accessories | Powerjack | Not Received
29 | 3M0078 C00 010 20 | B0300-450-E-ME-DG-124 | Pulley Bearing Housing | Elecon | Not Received
30 | 3M0078 C00 452 02 | B0300-450-E-ME-DG-122 | GA Drawing & Data Sheet of Travelling Trolley (Tripper Structure) | Elecon | Not Received

## Lub. Schedule
thyssenkrupp Industries India Pvt. Ltd.
Document Name |  |  | : Lubrication Schedule
Project |  |  | : TATA Steel Vertical Storage yard & equipment-RMHS
Client |  |  | : Tata steel Kalinganagar - TSK | [13 empty] | Rev | 0 Draft
Package |  |  | : Equipment and RMHS Package For TATA Steel Vertical Storage yard & equipment | [13 empty] | Date: | 2024-06-10
SL NO. | WSB NO. (To be filled by tkII) | EQUIPMENT | EQUIPMENT / CONVEYOR NO. | EQUIPMENT QUANTITY (Nos.) | EQUIPMENT MODEL NO. | PARTS TO BE LUBRICATED | PERIOD / LUBRICATION INTERVAL (Hours/ week / month / yearly) |  |  | NUMBER OF LUBRICATION POINTS | LUBRICANT SPECIFICATION AS PER MAKE | LUBRICANT BRAND/MAKE | QUANTITY (per unit) (Litres / Kg) | TOTAL QUANTITY (Litres / Kg) | FLUSHING QUANTITY (Litres / Kg) | TOTAL FLUSHING QUANTITY (Litres / Kg) | DRAIN FREQUENCY | SCOPE OF SUPPLY | INITIAL FILL (YES / NO) | REMARKS
[7 empty] | TOP UP | FIRST CHANGE | FURTHER CHANGE
1
2
3
4
5
6
7
8
9
10
11
12