## Rev.0
OWNER : |  | TATA STEEL | PROJECT : | TATA STEEL, KALINGA NAGAR
|  |  | PACKAGE : | TSK COAL VERTICAL STORAGE YARD EQUIPMENT
SUPPLIER : |  | TKIL Industries Pvt. Ltd. Pimpri, Pune - 411 018 | DOCUMENT TITLE : | GA of coiler and De-coiler (Belt Changing Device)
|  |  | TSL DOCUMENT NUMBER : | TSK-MDW-17-03-01-03-216-00014
- | - | - | tkII DOCUMENT NUMBER : | 3M0082 Y50 000 01
|  |  | REVISION : | 0
Sr. No. | Sheet No. | TATA STEEL comments dated : 30.09.2024 |  | TKIL/SYNERGY reply dated : 08.11.2024 | TKIL/SYNERGY reply dated : 06.12.2024 as per meeting with TSL dtd. 14/11/2024 over teams | TATA STEEL comments dated : 17.07.2025 | TKIL/SYNERGY reply dated : 17.07.2025
1 | 1/1 | Please submit the calculation for shaft considering weight & belt pull for elliptical type belt roll. |  | Shaft calculation is attached. | M/s Synergy have informed that the calculations will be submitted after GA drawing approval.
2 | 1/1 | Please indicate the elevation views of belt changing for all the conveyors (starting from cc-04 modified to cc-8f) to ensure the feasibility. |  | This is under review with M/s TKIL for feasibility check. Shall inform separately. | Please find attached individual conveyor drawings with belt changing device arrangment being shown.
3 | 1/1 | Please consider elliptical type belt coils/rolls also. |  | Elliptical type belt coils/rolls are considered. | Elliptical type belt coils/rolls are considered.
4 | 1/1 | Drives wil be required for both belt coiler & de-coiler. Please do the needful. |  | Drive for Decoiler is not required. New belt spool can be directly fitted on the decoiler. | Drive for Decoiler is considered. Price implication is there. Please see attached offer. (Belt Changing Device-Offer - PBU.pdf)
5 | 1/1 | Please submit the calculation on belt pull & power calculation. |  | Belt pull and power calculation are attached. | M/s Synergy have informed that the calculations will be submitted after GA drawing approval as its part of detail engineering.
6 | 1/1 | Winch system won't be required. |  | Winch is provided to pull the old belt to the coiler and new belt to the conveyor. | Winch system won't be required.
7 | 1/1 | M/s tkil to provide all the necessary inputs (weight, dimensions etc.) Related to elliptical type belt rolls to m/s synergy by collecting the same from belt manufacturers/supplier. |  | M/s TKIL supply for both EP and steel cord belting suppliers have confirmed circular type belt rolls for this project. However, based on the elliptical belt rolls inputs received from M/s TSL, M/s Synergy have revised the drawing. | Please refer revise drawing with elliptical roller shown in de-coiler view.
8 | 1/1 | Please provide mechanism to rotate the belt changing device upto 360deg. (by means of slew bearing) which will make it flexible to operate at any kind of adverse location. |  | As the coiler and decoiler for all the conveyors are placed properly the rotating arrangement for coiler/ decoiler is not required. | As per the feasilbility check of all conveyors, rotating arrangement is not required.
9 | 1/1 | Please submit calculations for bolt grade selection |  | M/s Synergy have informed that the calculations will be submitted after GA drawing approval as its part of detail engineering. | M/s Synergy have informed that the calculations will be submitted after GA drawing approval as its part of detail engineering.
10 | 1/1 | Please do not show any indicative view. Please show in line with comment no. 1 for all the conveyors. |  | This is under review with M/s TKIL for feasibility check. Shall inform separately. | Please find attached individual conveyor drawings with belt changing device arrangment being shown.
11 | [5 empty] | Drive at de-coiler is technical requirement. Can de-coiler operate without drive? M/s synergy to justify technically. | De-coiler can definitely be operated without drive. A separate write-up is attached for your reference & understanding. As per new requirement/comment of M/s TSL to include the drive for decoiler. hence the additional price was provided. Enclosed once again.
12 | [5 empty] | Why these items are being considered as additional items?
13 | [5 empty] | Please submit all the claculations as per crs sheet. | Shaft calculations enclosed. Balance calculations such as belt pull and power, bolt grade will be submitted after GA drawing approval as its part of detail engineering.
14 | [5 empty] | Please submit revised belt coiler & decoiler placement location in all the conveyor gad & plant layout drg. So that we can take final call on the requirement of slewing arrangement. | Enclosed
15 | [5 empty] | Plummer blocks shall be of tsl approved make. Please indicate the bearing nos. | The mentioned fabricated plummer block (Sr. no. 10 & 13 - GAD) with PB bush is Synergy's proprietary item. Since this is not a standard plummer block no manufacturer produces the same. This plummer block is a two halves plummer block fitted with PB bush for easy removal of the shaft.